## Cover Page
Big Data Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  |  | 2024-08-13
Project Team Name |  |  | Phân tích dữ liệu tài chính và thương mại điện tử
Project Topic |  |  | Recommendation System
Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 | [5 empty] | W2 | [5 empty] | W3 | [5 empty] | W4
[9 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24
[9 empty] | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14
1. Thu thập dữ liệu |  |  |  | 2024-07-22 | 2024-07-28 |  |  | Done | bar: 2024-07-22 to 2024-07-28
| 1.1 Thu thập dữ liệu trên Kaggle |  |  | 2024-07-22 | 2024-07-27 | Hải | Hải | Done | bar: 2024-07-22 to 2024-07-27
| 1.2 Đưa dữ liệu vô datawarehouse |  |  | 2024-07-27 | 2024-07-28 | Xuân | Xuân | Done | bar: 2024-07-27 to 2024-07-28
2. Tiền xử lý dữ liệu |  |  |  | 2024-07-29 | 2024-08-02 |  |  | Done | bar: 2024-07-29 to 2024-08-02
| 2.1. Xử lý dữ liệu thiếu,trùng |  |  | 2024-07-29 | 2024-07-29 | Thiện | Thiện | Done | bar: 2024-07-29
| 2.2. Tổng hợp dữ liệu |  |  | 2024-07-29 | 2024-07-30 | Thiện | Thiện | Done | bar: 2024-07-29 to 2024-07-30
| 2.3. Chuẩn hóa dữ liệu |  |  | 2024-07-30 | 2024-07-31 | Thiện | Thiện | Done | bar: 2024-07-30 to 2024-07-31
| 2.4. Xử lý dữ liệu thừa |  |  | 2024-07-31 | 2024-08-01 | Thiện | Thiện | Done | bar: 2024-07-31 to 2024-08-01
| 2.5. Giảm chiều dữ liệu |  |  | 2024-08-01 | 2024-08-02 | Thiện | Thiện | Done | bar: 2024-08-01 to 2024-08-02
5. Phân tích dữ liệu |  |  |  | 2024-08-02 | 2024-08-06 |  |  | Done | bar: 2024-08-02 to 2024-08-06
| 4.1. Phân tích dữ liệu đơn hàng |  |  | 2024-08-02 | 2024-08-06 | Thảo | Thảo | Done | bar: 2024-08-02 to 2024-08-03
| 4.1. Phân tích dữ liệu khách hàng |  |  | 2024-08-02 | 2024-08-06 | Thảo | Thảo | Done | bar: 2024-08-03 to 2024-08-04
| 4.1. Phân tích dữ liệu sản phẩm |  |  | 2024-08-02 | 2024-08-06 | Thảo | Thảo | Done | bar: 2024-08-04 to 2024-08-06
4. Xây dựng mô hình dự đoán |  |  |  | 2024-08-02 | 2024-08-07 |  |  | Done | bar: 2024-08-02 to 2024-08-06
| 3.1. Chia tập dữ liệu |  |  | 2024-08-02 | 2024-08-02 | Xuân | Xuân | Done | bar: 2024-08-02
| 3.2. Mô hình SVD |  |  | 2024-08-03 | 2024-08-06 | Xuân | Xuân | Done | bar: 2024-08-03 to 2024-08-05
| 3.3. Mô hình KNN |  |  | 2024-08-03 | 2024-08-06 | Xuân | Xuân | Done | bar: 2024-08-05 to 2024-08-06
| 3.4. Test mô hình |  |  | 2024-08-07 | 2024-08-07 | Xuân | Xuân | Done | bar: 2024-08-07
5. Deploy mô hình lên web |  |  |  | 2024-08-06 | 2024-08-10 |  |  | Done | bar: 2024-08-06 to 2024-08-10
| 5.1. Xây dựng web |  |  | 2024-08-06 | 2024-08-08 | Phước | Phước | Done | bar: 2024-08-06 to 2024-08-08
| 5.2. Đưa mô hình lên web |  |  | 2024-08-08 | 2024-08-10 | Trí | Trí | Done | bar: 2024-08-09 to 2024-08-10
6. Viết báo cáo |  |  |  | 2024-08-11 | 2024-08-14 |  |  | Done | bar: 2024-08-11 to 2024-08-14
| 6.1. Viết báo cáo phần 1 |  |  | 2024-08-11 | 2024-08-12 | Phước | Phước | Done | bar: 2024-08-11 to 2024-08-12
| 6.2. Viết báo cáo phần 2 |  |  | 2024-08-11 | 2024-08-12 | Trí | Trí | Done | bar: 2024-08-11 to 2024-08-12
| 6.3. Viết báo cáo phần 3 |  |  | 2024-08-11 | 2024-08-12 | Xuân | Xuân | Done | bar: 2024-08-11 to 2024-08-12
| 6.2. Làm silde thuyết trình |  |  | 2024-08-13 | 2024-08-14 |  |  | Done | bar: 2024-08-13 to 2024-08-14
|  | 6.2.1.Phần 1 |  | 2024-08-13 | 2024-08-14 | Hải | Hải | Done | bar: 2024-08-13 to 2024-08-14
|  | 6.2.2.Phần 2 |  | 2024-08-13 | 2024-08-14 | Thảo | Thảo | Done | bar: 2024-08-13 to 2024-08-14
|  | 6.2.3.Phần 3 |  | 2024-08-13 | 2024-08-14 | Thiện | Thiện | Done | bar: 2024-08-13 to 2024-08-14
Formulas:
End date = [Start date]+5
End date = [Start date]
Start date = [End date, row above]
Start date = [Start date, row above]+1

## Note
// THÔNG BÁO //
Ban tổ chức thông báo đến sinh viên về việc nộp dự án cuối khóa (Capstone Project) - SIC 2024, cụ thể:
Các nhóm sinh viên thực hiện đề tài với Giảng viên hướng dẫn đến hết ngày 14/08/2024
(bao gồm viết kế hoạch hành động [Action Plan], phân công công việc của từng thành viên [Work Breakdown], viết báo cáo tổng kết (Final Report) và chuẩn bị slide để thuyết trình [Presentation] dự án cuối khóa trước hội đồng chấm)
Xem các tài liệu mẫu tại: [ https://tinyurl.com/3nkyksrf ]
Ngày 15/08/2024, các nhóm sẽ nộp file mềm toàn bộ tài liệu nêu trên về cho Ban tổ chức theo đường link BTC cung cấp [ https://forms.gle/73s1pFVcfacx1mPPA ].